## Home page
TRUJET AIRLINES
Version No: |  |  |  | Verified By:Rugma Raghav
Tested By:YADHUKRISHNAN K |  |  |  | Date:24/1/2023
Os:Android |  |  |  | Browser name:
Test Id: | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
HOME PAGE
TA_HP_01 | Check whether the website launching properly when click on the link | 1.click on the link 2.look on the screen | https://www.yatra.com/domestic-airlines/trujet-airlines.html | should launch the website | properly launching the application | pass
TA_HP_02 | check whether the logo displayed is correct | 1.click on the link 2.look at the logo | https://www.yatra.com/domestic-airlines/trujet-airlines.html | logo should be displayed correctly when opening the website | logo displayed correctly when opening the website | pass
TA_HP_03 | check whether all the tabs are working in the home page | 1.open the website 2.click each tabs in the page |  | all tabs should work properly | All tabs are working properly | pass
TA_HP_04 | check whether all the labels and text fields are visible and they are in standard dimension as mentioned in SRS document | 1.open the website 2.look on to the labels and all text fields |  | labels and text fields should clearly visible and the dimensions are same as in the srs document | labels and text fields are clearly visible and the dimensions are same as in the srs document | pass
TA_HP_05 | check whether the search flights are redirected to respective page while clicking | 1.open the website 2.click on search flights button |  | search flights hould be redirected to respective page while clicking | search flights are redirected to respective page while clicking | pass
TA_HP_06 | check whether pages have any broken images | 1.open the website 2.look in to the screen for any broken images |  | should not have any broken images | doesnot have any broken images | pass
TA_HP_07 | check whether pages have any broken links | 1.open the website 2.look in to the screen for any broken links |  | should not have any broken links | doesnot have any broken links | pass
TA_HP_08 | check whether user can select class and no of travellers | 1.open the website 2.select travellers,class |  | should select travellers no and class | can easily select no of travellers and class | pass
TA_HP_09 | check whether user can enter alphabets in the from and to fields | 1.open the website 2.click on from and to fields 3.enter alphabets | test name/ delhi kochi | user can must enter alphabets in the from and to fields | user can properly enter alphabets in the from and to fields | pass
TA_HP_10 | check whether user can select suitable date in departure and return fields | 1.open the website 2.click on departure and return fields 3.select dates |  | should select suitable dates in daparture and return fields | user can select suitable dates in daparture and return fields | pass
TA_HP_11 | check whether it showing suggestions while typing in from and to fields | 1.open the website 2.click on from and to fields 3.fiil the fields | test name/ delhi kochi | should display suggestions while typing on from and to fields | properly displaying display suggestions while typing on from and to fields
TA_HP_12 | check whether user can add feedback | 1.open the website 2.click on ask questions | test questions | should add feedback | user can easily add feedback | pass
TA_HP_13 | check whether the social media logos are redirecting to their respective pages | 1.open the website 2.click on social media icons |  | should be redirected to respective platforms when clicking | properly redirecting to respective platforms when clicking | pass
TA_HP_14 | check whether it showing proper list of flights and respective prices | 1.open the website 2.click on flights list |  | must display list of flights and prices | properly showing flight list and prices | pass
TA_HP_15 | check whether user can select domestic andpopular flights | 1.open the website 2. click domestic and popular flights |  | must select domestic and popular flights | user can easily see the domestic and popular flights | pass
TA_HP_16 | check whether from and to fields are changing when directing to next page | 1.open the website 2.select from and to fields 3.fill the fields | test / delhi kochi | from and to fields should not be change | from and to fields are changing when directing to next page | fail
TA_HP_17 | check whether it showing starting prices of each flights | 1.open the website 2.select from and to fields 3.fill the fields 4.search flights | test / delhi kochi | should be display starting price of each flight | user can see starting price of each flight | pass
TA_HP_18 | check whether it showing running dates of each flights | 1.open the website 2.select from and to fields 3.fill the fields 4.search flights | test / delhi kochi | should dispaly runnung dates of each flight | properly showing the running dates of each flight | pass
TA_HP_19 | check whether user can select airline routines | 1.open the website 2.select airline routines |  | user should select all list of airline routines | user can easily select airline routines | pass
TA_HP_20 | check whether discount promo code is shown or not | 1.open the website 2.click on discount promocode |  | promo code should work properly | promo code doesnot working properly | fail

## Booking list
TRUJET AIRLINES
Version No: |  |  |  | Verified By:Rugma Raghav
Tested By:YADHUKRISHNAN |  |  |  | Date:24/01/2023
Os:Android |  |  |  | Browser name:
Test Id: | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
BOOKING LIST
TA_BL_01 | check whether user can sort flights accoeding to prices | 1.open the website 2.select the from and to fields 3.fill the fields 4.search for flights 5.select price | test name/ delhi kolkatha | should sort flights according to prices | user can easily sort flights accordung to prices | pass
TA_BL_02 | check whether the departing and arriving time are correct | 1.open the website 2.select the from and to fields 3.fill the fields 4.search for flights | testdata | departing and arriving time should be correct | departing and arriving time is not correct | fail
TA_BL_03 | check whether user can view remaining seats for each respective prices | 1.open the website 2.select the from and to fields 3.fill the fields 4.search for flights | test data | should view remaining seats according to repective prices | user can easily view remaining seats according to respective prices | pass
TA_BL_04 | check whether user can select stops | 1.open the website 2.select the from and to fields 3.fill the fields 4.search for flights 5.select stops | testdata | should select stops | user cannot select stops | fail
TA_BL_05 | check whether uer can view fares of each flight | 1.open the website 2.select the from and to fields 3.fill the fields 4.search for flights 5.select view fares | test data | user should view fares of different classes | properly viewing the prices of different classes | pass
TA_BL_06 | verify that user can select suitable dates according to user | 1.open the website 2.select the from and to fields 3.fill the fields 4.search for flights 5.select dates | testdata | should select different dates | user can select different dates | pass
TA_BL_07 | check whether the todays offer code was working properly | 1.open the website 2.search for flights 3.click todays offer code |  | The discount promo code should work properly | The user promo code doesnot working properly | fail
TA_BL_08 | verify that social media icons are directing to respective pages when clicking | 1.open the website 2.click on search flights 3.click on social media icons |  | should be directed to respective platforms when clicking icons | properly directing to respective platforms when clicking icons | pass
TA_BL_09 | verfy user can view the flight details of each respective flights | 1.open the website 2.search for flights 3.click on flight details |  | should view details of each respective flights | properly showing the details of each respective flights | pass
TA_BL_10 | check whether how much kg luggage can afford | 1.open the website 2.select the from and to fields 3.fill the fields 4.search for flights 5.click on respective flights |  | should more than 12kg of baggage can afford | users can take about 15kg of luggage | pass
TA_BL_11 | check whether the meal is paid or not | 1.open the website 2.search for flights 3.click on respective flights |  | should view meal is paid or not | properly viewing that meal is paid or not | pass
TA_BL_12 | check whether the fee and taxes are affordable or not | 1.open the website 2.search for flights 3.click on respective flight |  | should view the fee and taxes for each flight | properly viewing fees and taxes of each flight | pass
TA_BL_13 | check whether user can select suitable seats | 1.open the website 2.select the from and to fields 3.fill the fields 4.search for flights 5.click on respective flights 6.select seats |  | should select suitable seats according to user | user can select suitable seats | pass
TA_BL_14 | check whether user can pay by different payment methods | 1.open the website 2.search for flights 3.click on respective flights 4.click on pay |  | there should be more than 2 or more payment options | user can easily pay through different payment methods | pass
TA_BL_15 | check whether there is any number to contact | 1.open the website 2.search for flights 3.click on respective flights |  | should be an official contact numbers for enquiries | there is no contact number for user to contact | fail
TA_BL_16 | check whether there is feedback or complaint option for users | 1.open the website 2.search for flights 3.click on respective flights |  | there should be an feedback option of users | there is not an feedback option for users | fail
TA_BL_17 | check whether there is option to cancel the ticket | 1.open the website 2.search for flights 3.click on respective flights 4.book flights 5.cancel the tickets |  | should be an cancel option for users | users can easily cancel ticket | pass
TA_BL_18 | check whether user can changing the class after booking | 1.open the website 2.search for flights 3.click on respective flights 4.book the tickets 5.change the class |  | should be change the class after booking the flight | users can change the class after booking the flight | pass
TA_BL_19 | check whether how much kg hand bag user can handle | 1.open the website 2.search for flights 3.click on respective flights 4.click on flight details |  | should be handle more than 5kg of hand bag | user can handle more than 5kg of hand bag | pass
TA_BL_20 | check whether the cancellation is free or not | 1.open the website 2.search for flights 3.click on respective flights 4.click on flight details |  | cancellation should be paid or not | user can cancel tickets either paid or not | pass

## Sign up menu
TRUJET AIRLINES
Version No: |  |  |  | Verified By:Rugma Raghav
Tested By:YADHUKRISHNAN |  |  |  | Date:24/01/2023
Os:Android |  |  |  | Browser name:
Test Id: | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
SIGN UP MENU
TA_SU_01 | verify the contents of sign up form | 1.open the website |  | the contents of sign up page should be as per SRS document | the contents of sign up page is as per SRS document | pass
TA_SU_02 | verify the ui elements are visible and texts are readable | 1.open the website |  | UI elements in the sign up page should be visible properly and text in the page should be readable for users | UI elements in the sign up page is visible properly and text in the page should be readable for users | pass
TA_SU_03 | verify the input fields of sign up form are working properly | 1.open the website |  | input fields of sign up page should work properly | input page of sign up page is working properly | pass
TA_SU_04 | verify input field accepts alphabets | 1.open the website 2.enter alphabetic characters in the input field | test data | input field should accepts alphabets | input field accepts alphabets | pass
TA_SU_05 | verify input field accepts numbers and special characters | 1.open the website 2.enter numeric and special characters in the input field | 12345/ @#$% | input field should accepts numbers and special characters | input field accepts special characters and numbers | pass
TA_SU_06 | verify the number of spaces in between the inpur accepted in the name fields | 1.open the website 2.enter data in name field with no spaces 3.enter data in name field with 1 spaces 4.enter data in namr field with 2 spaces 5..enter data in namr field with 3 spaces | test/ test data/ test data new/ new test data value | name field should only accepts names with 2 or less spaces | name field accepts names with only 2 spaces | pass
TA_SU_07 | verify user can sign in with google or facebook | 1.open the website 2.sign in with google or facebook |  | should sigin in with google or facebook | can sign in with google or facebook | pass
TA_SU_08 | verify the data to the input fields are masked or not | 1.open the website 2.enter data to input field | test data | data entered in input field should be masked | input entered in input field is not masked | fail
TA_SU_09 | verify the case sensitivity of input field | 1.open the website 2.enter input with uppercase characters only 3.enter input with lowercase characters only 4.enter input with both uppercase and lowercase characters | TESTDATA/ testdata/ TESTdata | input field should accepts both lowercase and upper case characters | input field accepts both lowercase and uppercase characters | pass
TA_SU_10 | verify the working of continue button | 1.open the website 2.enter sign up with valid mail id or mobile number 3.click on continue button |  | should be redirected to OTP verification | redirecting to otp verfication page | pass
TA_SU_11 | check whether the continue functionality works with empty fields in the form | 1.click on website 2.empty the field 3.click on continue button |  | error message should be shown stating to fill field | error message shown | pass
TA_SU_12 | verify the error message is shown when entering invalid or non existing mail id or mobile number | 1.click on website 2.enter an invalid or non-existing mobile number click continue button | 123 | error message for invalid number should be shown | error message for invalid number is shown | pass
TA_SU_13 | verify the length of numbers accepted in mobile number field | 1.open the website 2.enter mobile number with less than 10 characters 3.enter mobile number with 10 characters 4.enter a mobile number with more than 10 characters | 12345/ 1234567890/ 123456789654 | mobile number field should only accepts 10 numbers | mobile number accepts only 10 numbers | pass
TA_SU_14 | check whether there is a show/hide icon near password input field and its working | 1.open the website 2.enter input to password field 3.click show/hide password icon |  | input entered in the password field should be visible and masked in alternative clicks on the icon | input entered in the password field is visible and masked in alternative clicks on the icon | pass
TA_SU_15 | verify the length of characters accepted in password field | 1.click on website 2.enter password less than 8 characters 3.enter password with 8-15 characters 4.enter password more than 15 characters | test/ newtestdata/ newtestdatapassword | password field should only accept password with 8-15 chatracters | password field accepts more than 15 characters | fail
TA_SU_16 | verify the combination of characters accepted in password field | 1.open the website 2.enter alphabetic characters in the password field 3.enter numeric characters only in password field 4.enter special characters only in password field 5.enter alphanumeric characters in password field 6.enter alphanumeric and special characters in password field | testpass/ 12345648/ @##$^&*/ testpass123/ testpass123@$ | password field should only accept input with alphabets,numbers and special characters | password field accepts input with alphabets,numbers and special characters | pass
TA_SU_17 | check whether a sign in button is present in the sign up page | 1.click on website |  | sign in button should present in the sign up page | sign in button is present in the sign up page | pass
TA_SU_18 | verify the create account button | 1.open the website 2.create account |  | user should redirected to account page | user is redirected to account page | pass

## Bug Report
TRUJET AIRLINES
Verified by:Rugma Raghav Identified by:YADHUKRISHNAN Reported to:Rugma Raghav Date:24-01-2023 Environment Details:Android
Bug id | Test Id: | Expected Result | Bug Description | Steps to reproduce | Severity | Priority | Screenshot | Status
BUG_TJA_01 | TA_HP_16 | From and to fields should no be change when directing to next page | From and to fields should are changing when directing to next page | 1.open the website 2.select from and to fields 3.fill the fields | major |  | https://drive.google.com/file/d/1YhzgXkkZinrcrbu22U7z9zX1mjLAVUxE/view?usp=share_link | new
BUG_TJA_02 | TA_HP_20 | Promo code should work properly | promo code doesnot working peoperly | 1.open the website 2.click on discount promo codes | minor |  | https://drive.google.com/file/d/1dh9Nji40KsTIvxro62AVS547nN4nb4W0/view?usp=share_link | new
BUG_TJA_03 | TA_BL_02 | departing time and arriving time should be correct | departing time and arriving time is not correct | 1.open the website 2.select the from and to fields 3.fill the fields 4.search for flights | major |  | https://drive.google.com/file/d/15gVbO_pvIcXNQvIvL5HP10dK6rbtVD8K/view?usp=share_link | new
BUG_TJA_04 | TA_BL_04 | user should filter the search results by selecting stops | user cannot filter the search results by selecting stops | 1.open the website 2.select the from and to fields 3.fill the fields 4.search for flights 5.select stops | critical |  | https://drive.google.com/file/d/1_iFYOv_YY7ZtsQnaK4VQM1oPuiupX4uX/view?usp=share_link | new
BUG_TJA_05 | TA_BL_15 | should be an official contact number for enquiries | there is no contact number for user to contact | 1.open the website 2.search for flights 3.click on respective flights | major |  | https://drive.google.com/file/d/1t09waK976VQhZms2SXuYaYqUFdmE9ZoX/view?usp=share_link | new
BUG_TJA_06 | TA_BL_16 | there should be an feedback option for users | there is not an feedback option for users | 1.open the website 2.search for flights 3.click on respective flights | minor |  | https://drive.google.com/file/d/1pDMchCGf67F1yqUqIJ1CpuesmEPhexyT/view?usp=share_link | new
BUG_TJA_07 | TA_SU_08 | Data entered in input field should be masked | Data entered in input field is not masked | 1.open the website 2.enter data in input field | minor |  | https://drive.google.com/file/d/1YvPPY7ITZhNzviWuuTvA6urrA3IgYBH6/view?usp=share_link | new
BUG_TJA_08 | TA_SU_15 | password field should only accepts password with 8-15 characters | password field accepts more with 8-15 characters | 1.click on website 2.enter password less than 8 characters 3.enter password with 8-15 characters 4.enter password more than 15 characters | major |  | https://drive.google.com/file/d/1-m47qT6aoSZm9VVJwvNPuQ0kQcljdwhN/view?usp=share_link | new

## Defect Distribution
Module name | Defect Distribution
Home page | 2
Booking list | 4
Sign up | 2

## Test Report
Module name | Test passed | Test failed | Total test
Home page | 18 | 2 | 20
Booking list | 16 | 4 | 20
Sign up | 16 | 2 | 18